## Slide 1: Order Out of Chaos: Uncovering Hidden Collections through Collaboration & Enhanced Discovery
Katie McCormick
Associate Dean of Libraries for Special Collections & Archives
Society of American Archivists 2014, Research Libraries Roundtable

## Slide 2: Ultimate Goals
For Manuscript and Archives Collections to
  Have complete online access
  Be fully searchable (at least at the collection level)
  Have coordinated representation in multiple access points
  Consistent, flexible metadata – whatever system we put information in we want to be able to migrate with the least number of steps
  Ability to market our collections and connect a variety of users to material

## Slide 3: Initial Issues
Collection information in multiple places but not necessarily consistent
No collection information available
Collection information only available through a physical visit to the reading room
Similarly named/ same named collections across areas
Lack on university archives structure
Difficult to connect researchers and others to our collections
We have not had a good understanding of these issues

## Slide 4: Breaking It Down
Identify
What has been done before?
Inventory
Starting at the source – using the Accessions book & spreadsheet to create an inventory list
Action
Phase 1 -
Can we use that work?
What is our most accurate, most comprehensive record?
What are our issues?
What do we know? What don’t we know?
Including Strozier, Pepper, and Heritage Protocol Collections
Listing Processed & Unprocessed Collections
Creating columns for all possible locations of information
Phase 2 –
Access findings /Defining future phases
What is our ultimate goal?
Compiling the spreadsheet
Review data
Compiling Information
Analyzing the data
Document ongoing & new issues / questions
Phase 3
Data migration & clean up
More in depth physical review
Review collections
Phase 4
Reorganization, Reprocessing, De-accessioning
Catalog clean up
Identify next system & desires for optimal finding aid display

## Slide 5: 2012 Special Collections & Archives
Strozier Special Collections Center
Heritage Protocol
Claude Pepper Library
1 FTE Librarians
1 FTE Archivist
1 FTE Professional staff
3 FTE staff
2 PTE staff
1 FTE Archivist
1 FTE staff
1 PTE staff
Intern
1 PTE staff

## Slide 6: 2014 Special Collections & Archives Division
Strozier Special Collections Center
Heritage Protocol / University Archives
Claude Pepper Library
Digital Library Center
Cataloging & Description
Digital Archivist
Metadata Librarian
Digital Studio Manager
2 FTE staff
1-4 PTE staff
4 FTE Librarians
4-5 FTE Staff
1-2 PTE Staff
Rare Books Librarian
Manuscripts Archivist
Collections Manager
1 FTE Staff
2 PTE Staff
2 Graduate Assistants (rotating)
1 Intern
Pepper Library Supervisor
1 FTE Staff
1 PTE Staff
Heritage Protocol/University Archivist
1 FTE Staff

## Slide 7
Accession Records
Handwritten Notebook
Review of different discovery systems
865 collections split among 21 staff members across division
Physical & Intellectual Review of “Problem” Collections
311 collections physically reviewed
Spreadsheets
Compiled into single spreadsheet of everything ever accessioned
Each person tasked with looking for collections information in 5 different systems & documenting findings in spreadsheets
Phase 1 – archivists reviewed collections to document needs
Did we still have these collections?
Did collections need to be reorganized? Reprocessed? De-accessioned?
1176 collections listed in final spreadsheet
Review completed in 3 weeks
4 week deadline
Notes: 1176 (total # of collection listings between MSS, Pepper, & HP)
  Not including
    113 unprocessed accessions
    28 listings for Oversize Map Case Collections
    53 listings for MSS-Newspapers
865 collections reviewed for access points
  Split between 21 people; review completed in 3 weeks
311 collections reviewed for arrangement issues & questions
  Split between 2 archivists, Eddie Woodward & Burt Altman

## Slide 8: Work Elements
Simple, dynamic access to archives & manuscripts
Data Clean Up and Consolidation
Physical Collection Review
Reorganization & Reprocessing of Collections
Cataloging & Clean-Up
Discovery Systems Review

## Slide 9: Key Players
Digital Archivist
University Archivist
Review
Analysis
Clean Up
Manuscripts Archivist
Collections Manager
Broader division staff

## Slide 10
Starting Point
Archon
Mid Point
Archon
Moving towards
ArchivesSpace
DigiTool
PALMM
Paper Only
“Old Website”
Library Catalog
Library Catalog
Paper Only
Library Catalog
? Dynamic online presentation of collection information

## Slide 11: Initial Results
Chart: 
| Items without Record | Items with Record | Items with Record + Link | Items with Record + Broken Link | Items with Record only | Items with Record + FA
Catalog | 361 | 593 | 299 | 105
Archives Florida | 639 | 320 | 17 | 303
DigiTool | 935 | 21 | 21 | 0
Archon | 218 | 739 | 530 | 210

## Slide 12: Steady Progress
Chart: 
| Archon Stub | Archon Full | Paper Only | No Catalog Record | No Access
2012 | 329 | 98 | 20 | 346 | 103
2014 | 857 | 586 | 3 | 324 | 33

## Slide 13: What We’re Discovering
Tracking & finding “missing”collections (started with 10, down to 5)
Preservation Issues
  Over and under filled boxes
  Inappropriate use of storage materials & supplies
  Acidic, damaged boxes
Administrative Issues
  Incorrect locations & extents
  Inconsistent naming between labels, documents, finding aids, etc.
  Folders from other collections mixed into boxes from physically close collections
  Collections of publications that should have been catalogued as serials and monographs
  Mislabeled collections
  Multiple parts of same collection accessioned as multiple collections across different areas
  Un-accessioned materials

## Slide 14: What’s Next?
Timeline for Archon data to be good enough to migrate
Exploration of ArchivesSpace
Discussions around our “next generation” finding aid delivery/display needs
Plans & timelines for reorganizing & reprocessing
Integrating digitization decisions into processing & review plans
Catalog Clean-Up
Data Migration