Society of American Archivists
Council Meeting Action List

(Version 022513)

| Action | Assigned To | Due Date | Status / Notes |
| --- | --- | --- | --- |
| 0113-II.B. ICA Representative: Query Peterson re value of SAA’s participation in ICA-SPA (“ICA 101”), weigh value against new strategic goals, other ways to be involved (eg, NAANICA); 0513 Action item for up/down vote. | McCrea, Dooley, Baxter | 4/24/13 | 0513 Action Agenda |
| 0113-II.C. AV Equipment for Roundtables: Inform RTs that they must complete AV request form; requests fulfilled based on availability of budgeted funds. | Beaumont to inform leaders, All to remind groups | 2/27/13 (Requests due 4/1) |  |
| 0113-II.G. SAAF Board: Issue call for Class B members (two vacancies in 2014) to diversify Board membership. Include specific criteria in call. | Bell-Russel, Beaumont | 12/1/13 |  |
| 0113-III.E. Strategic Planning: Complete draft plan: refined vision and mission statements; values list; and goals, strategies, and sample tactics. - Circulate draft of onsite work to Council. - Post comments on draft via discussion list. - Conduct Council conference call(s) to review high-level plan. - Small teams of Council members to develop tactics, send drafts to office for compilation. - Vet draft tactics via Council discussion list. - Distribute high-level plan, sample tactics to members for review and suggestions (including additional tactics). - Incorporate feedback into draft for 0513. - Distribute draft plan to members; solicit feedback broadly, encourage attendance at August forum. - Review and incorporate member comments; conduct Council discussions as appropriate; adopt new Strategic Plan by August/September. | Henrichs, Dooley, Beaumont All All Dooley to assign, All All Dooley, Beaumont Henrichs, Dooley, Beaumont Beaumont; All Henrichs, Dooley, Beaumont; All | 2/13/13 2/26/13 2/26/13 (schedule others as needed) 3/19/13 3/25/13 4/1/13 4/24/13 7/1/13 9/1/13 | 0513 Strategic Planning Agenda 0813 Action Agenda (or online disc/vote after 0813 meeting) |
| 0113-IV.B. FY 2013 B List: Provide canned tutorials, current budget to Council. Schedule follow-up conference call(s) as necessary. | Duffy, Jurczak, Beaumont | 2/8/13 |  |
| 0113-IV.C.1. Student/New Member Needs and Benefits – Revise Payment Options: Publicize broadly, change membership forms; post on OTR rationale for extending Bridge rate to two non-consecutive years over course of membership. | Staff; Dooley, Duffy | 2/15/13 | Publicized via website, ITL; forms changed. OTR posting of rationale necessary? |
| 0113-IV.D. NAANICA: Gather more info re value of NAANICA; consider in context of SPA and strategic planning view of international issues. Discuss with other orgs (eg, CoSA, NAGARA, ACA, ACA). | Dooley; All; Beaumont | 4/24/13 | 0513 Action Agenda (or online disc/vote) |
| 0113-IV.E. Regionals Summit: Use discussion list to maintain momentum, hash out group's goal(s). What type of organizational unit (within SAA) would serve goal(s), what type of meeting in 0813 would be beneficial? Emphasize ideas coming from bottom up in terms of how group may evolve. | McCrea, Baxter, Huth | 4/24/13 | 0513 Discussion Agenda |
| 0113-IV.F. Issues and Advocacy Roundtable: - Respond to I&ART’s concerns, explain Council rationale for not accepting recommendations. - Encourage I&ART to draft one or more issue briefs for Advocacy Agenda, collaborate with GAWG to bring forward to Council. - Encourage GAWG to draft workplan for developing issue briefs (with priorities), draft 2-3 briefs for Council consideration in 0513. - Revisit GAWG description and Advocacy Agenda at 0513 meeting. | McCrea McCrea, Zanish-Belcher, Beaumont Zanish-Belcher, GAWG, Beaumont Zanish-Belcher, All | 1/28/13 3/7/13 4/24/13 4/24/13 | 3/7/13 conference call scheduled with I&ART leaders, McCrea, Zanish-Belcher, NPB. 0513 Action Agenda 0513 Discussion Agenda |
| 0113-IV.H. Communications Task Force: Preliminary recommendations, due in 0513, should include member feedback. - Consider OTR post to launch feedback process. - Per NPB request: Post to discussion list favorite websites, likes/dislikes about SAA website, likes/dislikes about other websites. | Kaplan (Comm TF) Dooley, Kaplan All | 4/24/13 3/15/13 3/1/13 | 0513 Action Agenda |
| 0113-IV.J. Guidelines for Appointing Interns: Council decided not to adopt guidelines, but to leave decision re use of interns to board/committee chairs. - Develop talking points (based on draft guidelines, emphasizing opportunity for mentoring/career development) for distribution to chairs and via Leadership Resources page. - Review Governance Manual to standardize language re interns; add similar language to Working Group descriptions. | Bell-Russel, McCrea Baxter, Kaplan, Landis, Mueller | 3/1/13 4/1/13 |  |
| 0113-IV.K. SAA Records: Small group of Council members to work with UWM Archives, SAA staff rep, RMRT rep (to be solicited) to draft records retention guidelines for Council review/adoption in 0813. See 0113-IV.K. for details on scope of work. | Kaplan, Landis, McCrea, Doylen, Mueller, TBD | 7/15/13 | 0813 Action Agenda |
| 0113-IV.N. Council Exemplary Service Awards: Draft Wosh citation for 0513 meeting. [CONFIDENTIAL] | Landis, McCrea, Brinati | 4/24/13 | 0513 Action Agenda |
| 0113-IV.O. Boston College/IRA: Publish on website informational paper developed by GAWG, publicize broadly (while Oral History Section plans and implements related activities). | GAWG, Zanish-Belcher, Beaumont | 2/15/13 | DONE. DELETE. |
| 0113-IV.P. (Other) Proliferation of Roundtables: Prepare 0513 Discussion item re SAA's groups and resources and how to manage growth. | Meissner, Theimer | 4/24/13 | 0513 Discussion Agenda |
| 0113-IV.P. (Other) Governance Manual Review: Present summary of significant changes to content, full text revision, and access to tracked changes for online discussion and vote. | Baxter, Kaplan, Landis, Mueller | 4/1/13 | Online discussion/vote |
| 0113-V.I. Diversity Committee Report: Provide examples of "diversifying the archival record" to Zanish-Belcher for forwarding to Committee. | All | 2/15/13 | TZB to forward to Committee Huth’s 3 examples in 2/10 email message. DELETE. |
| 0113-V.M. 2013 Program Committee Report: Send to Schmuland (2014 co-chair) suggestions for topic areas to be added to 2014 Call for Proposals. | All | 4/1/13 | 2013 topic areas: access/privacy, advocacy, appraisal, archives history, audio/visual, description, digitization, diversity, education, electronic records, ethics, facilities/security, international, local interest, management, methodology, preservation, professionalism, records management, reference, social memory, standards, web access, other. |
| 0113-V.T. Section/Roundtable Annual Reports: - Use Consent Agenda for 0513 meeting to save time in addressing housekeeping items (eg, RT bylaws). - Review and respond to honoraria requests from RTs (VMCAR, WCRT) for 2013 Ann Mtg. | Dooley, Beaumont Duffy, Jurczak | 4/24/13 As received | 0513 Consent Agenda |
| 0113-V.U. External Representatives: Consider larger issues re external reps (eg, which to sunset, which external orgs should have reps) in light of strategic goals, gaps and inconsistencies uncovered by work done for 0812-1-II.C. | Dooley | 4/24/13 | 0513 (or 0813?) Discussion Agenda |
| 0812-1-II.A. ISO 16363 /Trustworthy Digital Repositories: Engage appropriate groups to develop education and implementation plan for this high-level best practice. (Motion 1) | Meissner/Standards Comm (Ed Comm, ERS) |  | Will be picked up by appropriate component groups as matter of course re Council-adopted standards. DELETE. |
| 0812-1-II.C. Reps to External Organizations: - Develop process for reviewing existing external representatives. - Propose to Gov Man review group for inclusion in Section XI for Council approval. - Work through current list of reps to recommend 1) termination or 2) changes to bring in line with Council-adopted guide-lines/procedures. | Landis, McCrea, Meissner | 4/1/13 for proposals to Gov Man group 4/24/13 for review of current list of reps | 0513 (or 0813?) Discussion Agenda (in coordination with 0113-V.U.) |
| 0812-To Do List: - Conduct up/down vote of Action List items prior to 0113. - Conduct up/down vote in light of strategic goals, strategies, and tactics. | Dooley / All Dooley / All | 12/1/13 4/24/13 | DONE. DELETE. Online prior to 0513 meeting. |
| 0812-1-IV.D.1. Treasurer: YTD Financials: Pending input from Communications TF, include in draft FY14 budget two scenarios for AO publication: 6x vs 4x per year. Consider advertising contracts. | Kaplan, Duffy, Finance Comm, Brinati | 4/24/13 |  |
| 0612-I.C. To Do List / SAA Born-Digital Records: - Revised language for 0112 #E8 -- Part 1: Information gathering: Conduct review of SAA Archives records retention schedule; conduct review of SAA website and other platforms containing digital content that is not scheduled for transfer to archives. Discuss with SAA staff what digital content is of particular concern for their work. Discuss with Doylen any plans for preservation of digital content and current capacity at UWM. Identify what digital content is at risk and merits preservation in native format (vs. printing out). Develop appraisal language for SAA's current digital content (if it doesn't exist already). Provide status updates to Council list. [Ref: 0612-I.C. 0112 To Do List, #E8 revised language / Part 1] - Part 2: Identify appropriate strategies. Once we have a better sense of what content exists that needs to be preserved in digital formats (if any) and what tools are already available at UWM, identify potential tools (trusted digital repository? Web crawling? Printing content?) and associated resources. Based on that and further consultation with UWM and SAA staff, develop recommendations for presentation to the Council. [Ref: 0612-I.C. 0112 To Do List, #E8 revised language / Part 2] |  |  | Superseded by 0113-IV.K. SAA Records. DELETE. Superseded by 0113-IV.K. SAA Records. DELETE. |
| 0612-III.A. FY13 Budget: Request funding from SAAF for ICA travel. If declined, fund attendance to fall meeting from operations budget, add spring meeting to B List. | Beaumont, Jurczak | 6/15/12 | Funding declined by SAAF. Both FY 13 meetings to be funded out of operations. DELETE. |
| 0612-III.A. FY13 Budget: Include B List on 0812 agenda (when Ann Meeting financials are more solid). | Duffy, Jurczak, Beaumont | 0113 Agenda | DONE 0113-IV.B. DELETE. |
| 0612-IV.A. Advocacy Agenda: Prepare issue briefs. | GAWG | Ongoing | Superseded by 0113-IV.F. action items. DELETE. |
| 0612-III.A. FY13 Budget: Follow up with Matienzo re web hosting services. | Staff | 0113 Agenda | Ongoing role of staff to monitor costs associated with hosting services, select vendors. DELETE. |
| 0612-III.F. S/RT Policies: Ensure A&A List policy includes language precluding job listings similar to that for RTs. | Beaumont | 0113 Agenda | DONE 0113-II.B. DELETE. |
| 0612-IV.F. ICA/SPA Rep: For 0113 Agenda: Include information from August 2012 rep report, work with ACA to develop rep selection criteria, reporting requirements; include sunset review of SAA's commitment. Determine funding source(s) for FY13, depending on number of meetings funded and response from SAAF. | Dooley, Beaumont, ACA | 0113 Agenda | DONE 0113-II.B., IV-B., V.U. DELETE. |
| 0612-IV.G.2. Leadership Forum: - Include discussion of 2013 Forum on 0113 Council agenda. - First-year members to develop plan for Council review prior to 0513 meeting (to allow for publicity beginning as early as possible). | Dooley, Beaumont Huth, Light, Zanish-Belcher | 0113 Agenda Prior to 0513 | DONE 0113-IV.M.2. DELETE. (Remove from Action list and add to Council Reminders.) Online discussion prior to 0513. |
| 0612-IV.H. NAGARA MOA: Council group to draft prospectus on future joint meetings, considering questions posed in IV.H., preliminary and ongoing recommendations of Annual Meeting TF, with report to 0513 meeting. | Dooley to make assignments | 4/24/13 | Kaplan, Landis, and Theimer served (with Cline) on group that drafted 0612-IV.H. No evidence that assignments were made. 0513 Action or Discussion Agenda |
| 0112-II.A. Strategic Plan / Diversity, DO#2: Use epubs or AA Online supplement to plan and implement 5- to 15-page case studies on diversity of archival record. Communicate assignment to Diversity Committee chair and encourage other SAA groups to participate (CHWG; NAART). | Zanish-Belcher, Diversity Comm, Brinati as appropriate | 0113 Agenda | DONE 0113-V.I. DELETE. |
| 0112-III.C. "Occupy" Movement: I&ART to investigate/monitor status of archives and library materials generated by Occupy Movement and report findings and recommendations to 0812 Council meeting. Consider linking case study to Code of Ethics. | McCrea, I&ART | 0113 Agenda | DONE 0113-IV.F. DELETE. |
| 0112-III.G. CPWG: Invite group to review Diversity DO#3 and prioritize five activities, beginning with development of list of core texts; report to 0113 Council meeting. | McCrea, CPWG | 0113 Agenda | DONE 0113-V.Q. DELETE. |
| 0111 Summit of National Organizations: Reach out to ALA and AAM to explore opportunities for collaboration. | Dooley, Beaumont |  | Ongoing. DELETE. |
| STUDENT ISSUES TO PRIORITIZE: |  |  |  |
| 0812-1-III.B. SNAP and Student Benefits: - Finance Comm to review SNAP suggestions re dues/registration fees; consult Memb Comm and others; report to 0113 meeting. (Motion 9) - Run numbers and provide existing models for Finance Comm discussion. 0812-1-III.C. Student Needs: Review member survey for data from student responses; report to Council what, if any, issues should be considered to address student member needs; suggest actions. 0812-1-III.C. Student Needs: Survey student chapters to determine chapter needs, include query for 5-year enrollment data to begin to gauge changes in “universe.” 0612-IV.I. Student Chapters / Liaisons: Contact all faculty advisors and chapter leaders (if possible), update chapter info on SAA website; serve as informal chapter liaisons until survey results are reviewed and other options are explored. 0612-IV.I. Student Chapters / Liaisons: - Survey student chapters / advisors via simple form in fall 2012. Include perspectives of Memb Comm and SNAP. Vet questions with Council. Report survey results at 0113 meeting. - Add "student chapter liaisons" to 0113 Council agenda. 0612-IV.I. Student Chapters / Liaisons: Develop discussion item on student councilor for 0812 Agenda. (Originally assigned to Baxter, Landis, Felker, Theimer.) 12/3/12 Council online discussion list re strategic priorities: (1) Change SAA bylaws so that SNAP is able to appoint one member to SAA Council to represent students and new professionals. 0112-I.C. 0811 To Do: Review Governance Manual for explicit assignment of Treasurer as Student Chapter liaison; modify as necessary. Adjust Student Program Subcommittee structure, calendar, and guidelines per 0612 Council discussion. Consider how to manage liaison assignment. Per C43: Develop written procedures for process to review and select student papers and posters. 0112-IV.E.2 New Member/First Timer Orientation: - Gather tips for navigating SAA and getting the most out of Annual Meeting; compile; develop handout for Orientation. Review AO article from Maryland student re good experience. (Originally assigned to Membership Committee, Baxter, Theimer, Beaumont.) - Consider involving SNAP RT and/or SAA Fellows. (Originally assigned to Membership Committee.) 0510-Membership: Investigate the answer to "What is our universe of archives students?" | Duffy, Jurczak Duffy, Jurczak Membership Comm, Baxter, Beaumont Beaumont Beaumont; All Beaumont Dooley, Beaumont Baxter, Kaplan, Landis, Mueller Baxter, Beaumont, Membership Comm Beaumont, Membership Comm Membership Comm, Beaumont | 0113 Agenda 0113 Agenda 0113 Agenda 0113 Agenda 0113 Agenda 0113 Agenda 0113 Agenda | DONE 0113-IV.C.1. DELETE. DONE 0113-IV.C.1. DELETE. As reported in 0113-IV.C.2, not currently possible given Membership Comm priorities. Reassign? Delete? As reported in 0113-IV-C-3, ongoing pending temporary staff support. As reported in 0113-IV.C.3, ongoing pending temporary staff support. As reported in 0113-IV-C-3, ongoing pending temporary staff support. Pending outcome of survey. Per Huth, Landis, Meissner comments in review of Action List: DELETE. Manual reviewed, adjustment ongoing. Re Student Program Subcommittee liaison: DONE 0113-IV.C.5. DELETE. Pending: How to manage student chapter liaison assignments. Beaumont working with SNAP leaders on pre-meeting orientation guide, coordinating with Membership Committee to ensure integration of SNAP ideas. DELETE. May be achieved via student chapter surveys. DELETE. |
| REGIONAL ITEMS TO PRIORITIZE: |  |  |  |
| 0112-IV.C. Regional Summit: Maintain communication after Summit; consider venue in which those who couldn't attend can participate. (Assigned to Summit Planning TF.) 0112-IV.C. Regional Incentives: Consider $50 membership in future for those who have never been members (no lapsed) but attended 2012 meeting. (For 0113 Agenda. Originally assigned to Staff and Baxter, Dooley, Cline. Beaumont, Council) | McCrea, Beaumont Beaumont | Ongoing Ongoing | Discussion list created. 2013 Summit scheduled. See 0113-IV.E. DELETE. Reduced dues requires constitutional amendment. Staff to offer meeting registration incentives on ongoing basis. DELETE. |