## Slide 1: EAD Revision Plan

## Slide 2
TS-EAD Created
February 2010
2010 Annual Meeting
Timeline for revision
Initial goals

## Slide 3: Initial Revision Timeline
October 2010: Call for comments
February 28, 2011: Deadline for comments
August 2011: Discussion forum at SAA Annual Meeting
Spring 2012: Working meeting of TS-EAD
December 2012: Release of draft schema for testing and comment
August 2013: Publish revised version

## Slide 4: Initial Goals
Issue a call for comments
Pursue funding to support the revision
Schedule a working meeting
Plan a forum on the revision of EAD at the 2011 SAA Annual Meeting

## Slide 5
127 Comments

## Slide 6: Funding Support
Nationaal Archief of the Netherlands
Gladys Krieble Delmas Foundation
National Endowment for the Humanities

## Slide 7
Working Meeting:
March 7-9, 2012

## Slide 8
Revision Forum
[That’s you!]

## Slide 9: Working Meeting Prep
Digest comments
Share principles for revision
Further discussion and brainstorming
Subgroup recommendations
Conference calls

## Slide 10: Working Meeting Products
Update/Summary for distribution
Roadmap for Schema Development Team
Name?

## Slide 11: Principles for Revision
Migration Path
Interoperability
Interchange

## Slide 12: Migration Path
The revision of EAD will support the migration of data from finding aids encoded in EAD 2002 (DTD and Schema)

## Slide 13: Interoperability
The revised EAD will interact with other standards in standardized and transparent way.
  Better support the semantics of relationships
  Simplify linking

## Slide 14: Interchange
The revised EAD will privilege elements and design features that support data interchange over pure presentation.
  Simplify
  Avoid Ambiguity
  Promote more uniform and predictable use.

## Slide 15: Continuing Timeline
March 2012: TS-EAD Working Meeting
April 2012: SDT Working Meeting
Late 2012: Release draft schema
Winter 2012/2013: Second comment period
Winter 2013: Tag Library editorial team meeting [subject to funding]
Summer 2013: Publish revised EAD